## Scrum Meeting Summary
Sprint 1
Day of Sprint | Date | Tasks Completed | Tasks Planned | Blockers
1 | 2025-11-05 | One person made the Git repo and made project folder and branches; others cloned, downloaded dependencies. Made sure everyone has the same versions. | Start with database setup (basic tables) and begin work on the Login Screen. | None.
2 | 2025-11-06 | Started with database, basic tables, worked on login screen. | Complete the Login Screen, begin the Registration Screen, and define database procedures for authentication. | Technical Blockers: Faced Oracle issues and were unable to connect; also had yarn and npm inconsistencies.
3 | 2025-11-07 | Made login and registration screen and procedures for the database. | Finalize Login/Registration screens and begin work on the OTP and Forgot Password features, while resolving persistent Oracle issues. | Oracle Workaround: Were unable to connect to Oracle, so started writing SQL queries in the notepad for now and planned to consult TA to resolve the issues.
4 | 2025-11-08 | Weekend Break | Weekend Break | Weekend Break
5 | 2025-11-09 | Weekend Break | Weekend Break | Weekend Break
6 | 2025-11-10 | Login screen and registration screen created successfully; working on OTP + Forgot Password screen and backend for these features and resolved the Oracle issues. | Start working on the first Admin feature: Add Building, and write its necessary database procedures. | None.
7 | 2025-11-11 | Started working on the Add Building feature and wrote procedures for the respective features. | Begin the next Admin feature: Add Room, and write its procedures ensuring all constraints are considered. | None.
8 | 2025-11-12 | Implemented the Add Room feature + wrote procedures for this, ensuring all the constraints. | Fix any identified constraint issues (like room/building existence) and start connecting the Admin feature APIs to the frontend. | None.
9 | 2025-11-13 | Fixed the constraint issue for the Add Room feature; started connecting backend of Add Building, Add Building Incharge, Add Room with the frontend. | Connect the backend API for the Login feature with its frontend screen. | Constraint Issue: Identified some issues with the constraints; a room was being added even if the building didn’t exist.
10 | 2025-11-14 | Connected backend of the Login with the frontend. | Connect the backend APIs for Registration, Forgot Password, and OTP with their respective frontend screens. | None.
11 | 2025-11-15 | Weekend Break | Weekend Break | Weekend Break
12 | 2025-11-16 | Weekend Break | Weekend Break | Weekend Break
17 | 2025-11-17 | Connected backend for Registration + Forgot Password + OTP with the frontend. | Review the entire project, perform end-to-end testing, and prepare for Sprint 2 planning. | OTP Testing Block: Connection was successful, but there were issues with the OTP that was required for registration and forget password, so were unable to test that.
18 | 2025-11-18 | Reviewed the entire project with the implemented features. | Prepare final documentation and assets for the Sprint Review. | Email Dependency: Everything was working fine except for the things that required OTP from email.
Sprint 2
Meeting | Date | Tasks Completed (Yesterday) | Tasks Planned (Today) | Blockers
1 | 2025-11-24 | Backend procedures for Add Booking feature completed. Wrote procedure for posting and deleting announcements and wrote triggers for posting announcement. | Frontend development for Add Booking (Student) and resolving current database issues. Write procedures for showing announcements (for all users). | Database Synchronization Issue: Some team members were unable to see the latest database changes (procedures/tables).
2 | 2025-11-25 | Initial frontend development for the Student Add Booking feature completed. Wrote procedures for showing announcements from PO, students, and BI perspective. | Continue working on Student Add Booking validation and integration. Write procedures for cancelling bookings from PO and BI's perspective. | Connection Issue: Faced issues connecting the frontend booking form with the backend API, so the booking request wasn’t reaching the server.
3 | 2025-11-26 | Initiated change: Started work on adding Phone Number field to the Login feature + updated BE/DB fields. | Complete the Phone Number field implementation across Login and Registration flows. | Version Conflict: Found a version issue in server.js file (old syntax being used with updated dependencies).
4 | 2025-11-27 | Completed adding the Phone Number field to the Registration feature, including corresponding database updates. Wrote procedures for cancelling bookings from PO and BI's perspective. | Begin implementing the Room Booking frontend features for the Admin role. | None.
5 | 2025-11-28 | Completed initial frontend development for the Room Booking feature (Admin), including viewing available rooms. | Implement the Room Booking feature for the Building Incharge role. | None.
6 | 2025-11-29 | Weekend Break. | Weekend Break. | Weekend Break.
7 | 2025-11-30 | Weekend Break. | Weekend Break. | Weekend Break.
8 | 2025-12-01 | Began frontend development for the Room Booking feature (Building Incharge). | Complete the Building Incharge booking feature (including any required management views). | Testing Delays: Time slot formatting also caused delays in testing the create booking function.
9 | 2025-12-02 | Completed frontend development for the Room Booking feature (Building Incharge), including management views. | Final review, overall integration, and updating documentation. | Because the request wasn’t hitting the backend, the team couldn’t view the actual Oracle error or complete the booking flow.
| 2025-12-03 | Wrote procedures for showing reservation history to PO, students, and BI. | Completed Reservation History Display for all users (PO, Student, BI). Fixed time slot formatting issues entirely. | None.
10 | 2025-12-04 | Final Integration: Ran everything end-to-end. Updated all documents & test case results. | Sprint Review and Planning. | Wasn’t able to fully verify the booking creation end to end (consequence of earlier connection issues).
11 | 2025-12-05 | Completed all Sprint 2 deliverables. Final documentation sign-off and retrospective preparation. | Sprint Review Presentation and Retrospective. | None